PRE-INCORPORATION AND FINANCING DOCUMENT

Mbarara Integrated

Concrete Products Factory

Business Plan 2026-2035

Concept illustration of the planned lean facility; not evidence of an existing factory.

| STARTING CAPITAL | ESSENTIAL PHASE 1 COST | PROTECTED BUFFER |
| --- | --- | --- |
| UGX 130.0 Mio. | UGX 128.0 Mio. | UGX 2.0 Mio. |

| Prepared for | Founder | Location | Date |
| --- | --- | --- | --- |
| FAU Startup Advisory / Bianca Niemann | Hillary Arindamukama | Mbarara City, Uganda | 11 August 2026 |

CONFIDENTIAL - WORKING DOCUMENT FOR ADVISORY AND FINANCING PREPARATION

# Table of Contents

Table of Contents	2

1. Executive Summary	3

2. Founder, Mentor and Organisation	4

2.1 Planned Phase 1 Organisation	4

3. Company and Business Model	4

4. Customer Problem, Solution and Value	5

5. Market and Target Customers	5

5.1 Evidence Required Before Machine Ordering	5

6. Competition and Positioning	6

7. Product Portfolio and Phase 1 Priority	6

8. Product Mix Assumptions and Technical Validation	6

9. Production, Machinery and Capacity	7

10. Site, Layout and Logistics	7

11. Raw Materials, Supply and Inventory Control	8

12. Quality Management and Laboratory	8

13. Digital Management System	8

14. Legal, Tax and Regulatory Roadmap	9

15. Sales, Pricing and Payment Strategy	9

16. Sustainability and Impact	11

17. Implementation and Milestones	11

18. Phase 1 Investment Budget	12

19. Financial Model and Monthly Result	12

20. Break-even, Profit Target and Sensitivity	13

21. Financial Plan 2026-2035	14

22. Financing and Capital Strategy	16

23. Risk Register	16

24. Decision Gates and 90-Day Work Plan	17

25. Conclusion	17

Appendix A: Assumptions and Data Register	18

Appendix B: Sources	18

Appendix C: Verification and Disclaimer	18

# 1. Executive Summary

Mbarara Integrated Concrete Products Factory (MICPF) is a planned, phased manufacturer of concrete blocks, paving products and selected precast items in Mbarara, Western Uganda. Phase 1 deliberately focuses on a small number of regularly demanded products and one semi-automatic starter line. Capital-intensive additions such as owned delivery trucks, heavy lifting equipment, large culvert moulds, ready-mix concrete and a second production line will be introduced only after demand and positive cash flow are demonstrated.

The funding requirement is strictly capped at UGX 130,000,000. UGX 128,000,000 funds essential equipment, site preparation, opening inventory and market entry, while UGX 2,000,000 remains a protected liquidity buffer. Feasibility depends on securing a site without purchasing land, keeping machine and mould quotations within the stated limits, and using hired delivery vehicles during the launch period.

| Key metric | Value | Interpretation |
| --- | --- | --- |
| Monthly revenue at stable base utilisation | UGX 140.020.000 | Estimated; sales mix requires order evidence |
| Production and material cost | UGX 93.701.422 | Current integrated costing model |
| Gross profit | UGX 46.318.578 | 33,1% |
| Monthly operating expenses | UGX 14.100.000 | Labour, maintenance, administration and sales/logistics |
| Operating profit before tax | UGX 32.218.578 | 23,0% |
| Illustrative profit after 30% model tax | UGX 22.553.005 | Before depreciation, financing and reinvestment |
| System break-even revenue | UGX 42.623.977 | Assumes unchanged gross margin |
| Revenue for UGX 20m pre-tax profit | UGX 103.083.519 | Approximately 74% of base revenue |
| Revenue for UGX 20m model profit after tax | UGX 128.994.751 | Approximately 92% of base revenue |

Investment decision The model shows a credible opportunity, not a guarantee. Funding should be released only after site rights, three comparable machine and mould quotations, raw-material quotations, utility confirmation and initial customer letters of intent are documented.

Figure 1: Phase 1 use of funds. Total including the protected buffer is UGX 130,000,000.

# 2. Founder, Mentor and Organisation

|  | Hillary Arindamukama Founder and intended Managing Director International student at Friedrich-Alexander-Universität Erlangen-Nürnberg, studying B.Sc. Clean Energy Processes. Responsible for project leadership, strategy, financing coordination, business development and the integrated digital management platform. Email: arindahillary222@gmail.com |
| --- | --- |

Prakhar Singh is a mentor and professional sounding board. He is not presented as a co-founder, shareholder, director, authorised signatory or operating manager. Any later formal role requires a separate written agreement.

## 2.1 Planned Phase 1 Organisation

| Function | Primary responsibility | Staffing status |
| --- | --- | --- |
| Managing Director / Founder | Financing, strategy, partnerships and control | Hillary Arindamukama |
| Production supervisor | Daily plan, material usage, shift and machine control | Recruit locally before start |
| Machine operator | Mixing, mould changes, compaction and first-line control | Train before commissioning |
| QC / warehouse lead | Batches, curing, testing, stock and release | Combined launch role |
| Sales / administration | Quotations, customer files, invoicing and receipts | Lean part-time/shared role |
| General labour / safety | Handling, cleaning, pallets and site safety | Demand-led |

Governance principle Banking, procurement, discounts, customer credit and payments will have documented approval limits. Personal and business money will remain fully separate. The mentor has no ownership or signing rights without written authority.

# 3. Company and Business Model

MICPF is intended to be incorporated as a Ugandan private limited company. It will manufacture standardised concrete products, sell ex-factory and arrange site delivery for economically qualifying bulk orders through hired vehicles. Revenue will come from product margins, delivery charges and later project-specific manufacture. Credit sales will be limited to verified customers with approved limits.

| Building block | Phase 1 configuration |
| --- | --- |
| Value proposition | Reliable dimensions, documented mixing and curing, batch release and planned delivery |
| Customers | Contractors, hardware stores, developers, schools, hospitals, hotels, churches, NGOs, public projects and residential builders |
| Sales | Direct outreach, dealer partnerships, site visits, website/WhatsApp enquiries and disciplined follow-up |
| Production | Semi-automatic line, limited mould set, planned mould changes and demand-led schedules |
| Payment | Deposits for made-to-order work; balance before dispatch; credit only after checks |
| Logistics | Ex-factory pricing, hired trucks and free delivery only where bulk-order economics support it |
| Scaling | New moulds and products only against confirmed orders or retained earnings |

# 4. Customer Problem, Solution and Value

Concrete products in the target market are supplied by businesses with different levels of professionalisation. Builders can face variable dimensions, weak compaction, insufficient curing, absent batch records and unreliable delivery. MICPF addresses these risks through controlled production, recorded material use, defined hold/release status and transparent quotations and payment terms.

| Customer problem | MICPF response | Measurable evidence |
| --- | --- | --- |
| Variable product quality | Batch mixing and curing records | Test results, rejection rate and release status |
| Unreliable availability | Production and inventory planning | Confirmed order, committed delivery date |
| Unclear prices | Written UGX quotation with delivery and payment schedule | Quotation number and validity |
| Transport damage or delay | Route-based hired transport and documented handover | Dispatch plan and delivery note |
| Weak complaint process | Batch-linked complaint and corrective action | Traceable response by batch |

# 5. Market and Target Customers

Market entry will be validated bottom-up. This business plan does not use an unverified market-size claim. Demand will be established through quotation requests, dealer interviews, construction-site visits and customer letters of intent. The initial focus is Mbarara City and short delivery corridors, followed by Rwampara, Isingiro, Ntungamo, Bushenyi, Ibanda, Kiruhura, Sheema, Lyantonde, Kabale and Rukungiri.

| Segment | Need | Initial offer | Route to market |
| --- | --- | --- | --- |
| Contractors | Large scheduled quantities | 6/8-inch blocks, pavers and kerbstones | Direct visits and framework quotations |
| Hardware stores | Regular smaller releases | 6-inch blocks and standard pavers | Dealer terms with minimum order |
| Developers | Quality, timing and documentation | Blocks, pavers and kerbstones | Project quotation and delivery plan |
| Institutions | Building and external works | Blocks, 60 mm pavers; drainage later | Needs calendar and site meeting |
| Public/NGO projects | Documentation and formal procurement | Kerbstones, pavers; drainage later | Prequalification and tender monitoring |
| Residential builders | Price, advice and availability | Blocks and pavers | Website, WhatsApp and dealers |

## 5.1 Evidence Required Before Machine Ordering

At least 20 structured customer interviews in Mbarara and neighbouring districts.

At least five written purchase-intent letters or credible quotation requests.

Three price checks for every core product, each recording date, location, unit and delivery terms.

At least two potential hardware partners with a defined monthly minimum purchase.

Documented payment habits and accepted deposit levels by customer segment.

# 6. Competition and Positioning

The existing competitor list is a research starting point rather than a verified market study. Named businesses and local producers must be confirmed by telephone, website or social-media review, quotation or field visit. No market-share conclusion is drawn from the starting list.

| Competitor group | Examples from the starting list | Preliminary risk | Required check |
| --- | --- | --- | --- |
| Local block yards | Mbarara yards and BIMS Bloks Mbarara | High on price and proximity | Price, capacity, quality and delivery time |
| Paver/precast makers | iConic Concrete, Master Industries and Nicomah | Medium to high | Range, references and delivery area |
| Raw-material suppliers | Stone Providers Ltd and local quarries | Supply-chain relevance | Tonne price, moisture, weighing, credit |
| Cement distribution | Hima, Tororo, Kampala and Simba distributors | Supply relevance | Price, minimum order, delivery and credit |

MICPF will not position itself as the cheapest supplier. Differentiation will come from documented quality, reliable dimensions, planned curing, clear delivery commitments, traceable prices and professional complaint handling. Discounts will be exchanged for volume, deposits and efficient delivery routes.

# 7. Product Portfolio and Phase 1 Priority

| Product | Phase 1 status | Planned price | Strategic role | Data status |
| --- | --- | --- | --- | --- |
| 6-inch hollow blocks | Core | UGX 2,600/unit | Volume product for contractors and dealers | Estimated |
| 8-inch hollow blocks | Core | UGX 3,400/unit | Structural wall applications | Estimated |
| 60 mm pavers | Selective | UGX 2,400/unit | External works; only with confirmed margin | Quotation required |
| Kerbstones | Order-led | UGX 18,000/unit | High unit contribution, lower volume | Estimated |
| Solid blocks | Secondary | UGX 3,000/unit | Made only to verified demand | Estimated |
| 80 mm pavers | Secondary | UGX 3,200/unit | Heavy-duty surfaces; verify price | Quotation required |
| 4-inch hollow blocks | Conditional | UGX 1,800/unit | Only if mould is included or customer-funded | Estimated |
| Special pavers/drainage/culverts/ready-mix | Deferred | Quotation only | Only after proof of demand | Quotation required |

Clear launch rule The base revenue mix relies on 6-inch and 8-inch hollow blocks, 60 mm pavers and kerbstones. Solid blocks, 80 mm pavers and 4-inch blocks are made only against confirmed demand, protecting the UGX 130 million cap.

# 8. Product Mix Assumptions and Technical Validation

| Product | Working mix assumption | Release condition |
| --- | --- | --- |
| 4-inch hollow block | 1 cement : 6 stone dust | Trial mix, dimensions, strength and absorption |
| 6-inch hollow block | 1 cement : 7 stone dust | Trial mix, dimensions, strength and absorption |
| 8-inch hollow block | 1 cement : 6 stone dust | Trial mix, dimensions, strength and absorption |
| Solid block | 1 cement : 5 stone dust : 1 sand | Trial mix and application-based release |
| 60 mm paver | 1 cement : 3 sand : 3 aggregate | Strength, abrasion, dimensions and surface |
| 80 mm paver | 1 cement : 2.5 sand : 3 aggregate | Strength and heavy-load suitability |
| Kerbstone | 1 cement : 2 sand : 3 aggregate | Dimensions, edges, strength and handling |

These ratios are launch assumptions rather than certified recipes. The final recipe must be set for each material source through controlled trials. No strength or standards-conformity claim will be published before testing and the UNBS pathway are confirmed.

# 9. Production, Machinery and Capacity

The UGX 45,000,000 machinery allowance covers a semi-automatic block/paver machine, mixer and vibration equipment. The specific manufacturer is not yet selected. At least three written quotations must be compared on the same technical specification before an order is placed.

| Assessment criterion | Minimum evidence before deposit |
| --- | --- |
| Actual output | Guaranteed units by mould and eight-hour shift, not theoretical cycles only |
| Product changeover | Time, labour and waste during mould change |
| Power requirement | Motor rating, starting current, phases, protection and generator requirement |
| Moulds | Dimensions, material, service life and replacement cost |
| Service | Warranty, installation, operator training and response time |
| Spare parts | Critical wear parts held locally and lead time |
| Acceptance | Test production using local materials and defined QC checks |

| Product | Monthly quantity | Daily requirement at 26 days | Planned price | Monthly revenue |
| --- | --- | --- | --- | --- |
| 6-inch hollow block | 26,000 | 1,000 | UGX 2,600 | UGX 67,600,000 |
| 8-inch hollow block | 12,000 | 462 | UGX 3,400 | UGX 40,800,000 |
| 60 mm paver | 5,000 | 192 | UGX 2,400 | UGX 12,000,000 |
| Kerbstone | 1,000 | 39 | UGX 18,000 | UGX 18,000,000 |
| Delivery charges | - | - | - | UGX 1,620,000 |
| TOTAL | 44,000 units | Approx. 1,693 | - | UGX 140,020,000 |

Capacity gate The sales plan is released only if the selected supplier confirms the combined daily output after mould changes, cleaning, downtime and normal rejection.

# 10. Site, Layout and Logistics

The UGX 130 million plan contains no land purchase. It assumes a legally secured lease or use right for a suitable site in or near Mbarara. Before investment, the project must check heavy-vehicle access, drainage, power, water, neighbour separation, dust/noise control and expansion space.

Figure 2: Recommended material and quality flow. Final arrangement requires surveying, drainage planning and authority review.

Raw materials are separated, drained and protected from mixing.

Cement remains dry, locked and issued under dosage control.

Curing areas receive batch identification and controlled watering.

Finished goods move into saleable stock only after internal release.

Customer and delivery traffic remain separate from raw-material unloading.

No delivery truck is purchased in Phase 1; vehicles are hired by route or order.

# 11. Raw Materials, Supply and Inventory Control

| Input | Planned price | Primary control | Data status |
| --- | --- | --- | --- |
| Cement, 50 kg bag | UGX 36.000 | Brand, manufacturing date and dry storage | Estimated |
| Stone dust, tonne | UGX 45.000 | Grading, moisture and weighbridge evidence | Estimated |
| Sand, tonne | UGX 38.000 | Cleanliness, grading and moisture | Estimated |
| Aggregate, tonne | UGX 60.000 | Grading, strength and weighbridge evidence | Estimated |
| Electricity, kWh | UGX 780 | Tariff, connection capacity and meter | Estimated |
| Water, m3 | UGX 4.200 | Quality, availability and curing need | Estimated |
| Diesel, litre | UGX 6.600 | Delivery note and use by vehicle/generator | Estimated |
| Hired transport per truck | UGX 260.000 | Route, payload, return load and unloading | Estimated |

The UGX 26,000,000 opening-material allocation will not be spent at once. Purchasing will be released in tranches against confirmed orders and actual storage capacity. After the first production month, minimum stock, reorder points and consumption per product will be recalculated from measured data.

# 12. Quality Management and Laboratory

Quality is both the main point of differentiation and a material liability risk. Every production batch receives a batch ID, product description, operator, material quantities, mix ratio, water addition, production time, curing start, test status and release decision. Product on hold or failed status may not be dispatched.

| Test | Phase 1 method | Decision |
| --- | --- | --- |
| Dimensions | Measuring device/tape; batch sample | Pass, hold or rework |
| Visual defects | Edges, cracks, voids and surface | Reject or inspect again |
| Density | Mass and volume | Trend control |
| Water absorption | Defined laboratory procedure | Product-specific limit |
| Compressive strength | External accredited testing by product and age | Release against test plan |
| Curing age | Daily register and batch sign | No early sale |

Relevant standards include US 2032:2019 for hollow concrete blocks, US 2033:2019 for solid concrete blocks and US 65:2019 for precast concrete paving units. The mandatory scope and product-certification process will be confirmed with UNBS before conformity claims or formal market release. [S8-S10]

# 13. Digital Management System

The existing React and TypeScript platform links financial simulation, inventory, production, quality control, sales, expenses, market intelligence and reporting. It is currently a functional planning and demonstration prototype. Until productive PostgreSQL migration, formal access controls and accounting integration are completed, it does not replace audited accounting, statutory tax records or controlled quality documentation.

| Module | Business value | Go-live control |
| --- | --- | --- |
| Financial simulation | Price, cost and profit scenarios | Monthly reconciliation to evidence |
| Inventory | Stock, valuation, consumption and reorder levels | Physical count and dual control |
| Production | Daily output, materials, machine hours and rejection | Batch ID and supervisor release |
| QC/laboratory | Test results and certificates | Held product cannot be sold |
| ERP/sales | Customers, invoices, receipts and balances | Role permissions and daily backup |
| Market intelligence | Price and competitor monitoring | Source, date and confidence required |

Public website: https://mbarara-concrete-factory.pages.dev

Integrated platform: https://mbarara-concrete-platform.pages.dev

# 14. Legal, Tax and Regulatory Roadmap

The recommended structure is a Ugandan private limited company. Legal and tax implementation must be confirmed by qualified Ugandan advisers. Formalisation includes company registration, TIN, the relevant trading licence and all applicable site, environmental, labour and product requirements. [S5-S7]

| Authority/topic | Required action | Timing | Status |
| --- | --- | --- | --- |
| URSB | Check/reserve name and incorporate company | Before contracts and bank account | Open |
| URA | TIN, tax heads and record obligations | Before trade | Open |
| VAT/EFRIS | 18% standard rate; plan exceeds UGX 150m annual or UGX 37.5m three-month threshold; confirm registration and EFRIS | Before first taxable invoice | Critical |
| Mbarara City/local authority | Trading licence and planning/building/use approval | Before site operation | Open |
| NEMA | Determine Project Brief or ESIA requirement | Before works/installation | Open |
| MGLSD/OSH | Register workplace, safety systems and machinery inspection | Before commissioning | Open |
| UNBS | Obtain standards and confirm testing/certification pathway | Before conformity claims | Open |
| NSSF/PAYE | Establish employer and employee obligations | Before/at recruitment | Open |
| Insurance | Plant, liability, accident, fire and transport cover | Before production | Open |

Tax treatment The base model treats UGX 32,218,578 as operating profit before tax. A simplified 30% corporation-tax illustration leaves UGX 22,553,005. The standard VAT rate is 18%; until confirmed by an adviser, planned selling prices should be read as net prices before VAT. Actual taxable profit depends on depreciation, allowable deductions, VAT, financing and legal structure. [S11-S12]

EXIST is not a core funding route for the Uganda-only model because incorporation and commercialisation in Germany may be required. A German structure will be considered only if it has genuine operational and legal substance. StArfrica is treated as a networking, learning and investor-access channel; funding is not assumed.

# 15. Sales, Pricing and Payment Strategy

The launch will begin with a controlled list of specific buyers rather than broad advertising. Each opportunity will record product, quantity, location, decision date, payment capacity and delivery route. Prices are maintained in UGX. Planned prices are ex-factory and before VAT unless an adviser confirms another presentation.

Build a top-50 target-customer list for Mbarara City and neighbouring districts.

Contact ten decision-makers and visit at least five sites or dealers each week.

Issue quotations within 24 hours, showing validity and delivery conditions.

Require deposits for made-to-order products and the balance before loading.

Grant credit only after documented checks, limits and due dates.

Record the reason for every lost order: price, quality, lead time, relationship or finance.

Figure 3: Revenue mix under the stable base model. Every selling price remains subject to market confirmation.

# 16. Sustainability and Impact

Environmental positioning will be cautious and measurable. The project does not claim carbon neutrality. Initial contributions come from longer-lasting products, lower rejection, shorter regional delivery routes, controlled dosing, process-water reuse where technically acceptable and later permeable paving systems. Socially, the factory will create formal local jobs and improve dependable construction-material supply in Western Uganda.

| Impact area | Indicator | Phase 1 target |
| --- | --- | --- |
| Material efficiency | Rejection rate | Below 3% after month three, then reduce further |
| Quality | Batches with complete dataset | 100% |
| Water | m3 per 1,000 products | Measure from day one; set target after baseline |
| Energy | kWh per 1,000 products | Measure from day one; maintenance/load management |
| Employment | Formal local positions | Lean team, growing with secured sales |
| Supply chain | Share of regionally sourced inputs | Maximise subject to quality conformity |

# 17. Implementation and Milestones

| Period | Work package | Release criterion |
| --- | --- | --- |
| Days 0-30 | Site rights, customer interviews, quotation structure and three supplier quotations | Evidence folder complete |
| Days 31-60 | Company, TIN, bank account and site/environment/OSH pre-check | Legal and approval pathway confirmed |
| Days 61-90 | Machine decision, contract, mould list and site works | Budget not exceeded |
| Days 91-120 | Delivery, installation, power/water and recruitment | Acceptance and safety training |
| Days 121-150 | Trial mixes, test plan, rejection and capacity test | QC release for core products |
| Days 151-180 | Controlled market start and first deliveries | Deposits, positive contribution and batch records |
| Months 7-12 | Increase utilisation to 75-100% | Repeat customers and monthly management close |

# 18. Phase 1 Investment Budget

The following use of funds is the binding maximum for the starter project. Items marked quotation required may be committed only after written confirmation. The cash buffer is not a general purchasing allowance.

| Use of funds | Amount | Control |
| --- | --- | --- |
| Semi-automatic block/paver machine, mixer, vibrator | UGX 45.000.000 | Essential quotation required |
| Starter moulds: 6-inch, 8-inch, solid, 60 mm, 80 mm, kerbstone | UGX 14.000.000 | Essential only |
| Site preparation, curing yard, drainage, basic shed works | UGX 14.000.000 | Lean starter works |
| Electrical and water connection setup | UGX 7.000.000 | Essential utilities |
| Pallets, wheelbarrows, hand tools, racks, safety gear | UGX 8.000.000 | Starter handling |
| Starter raw materials and packaging | UGX 26.000.000 | Working stock |
| Permits, basic laboratory tools, compliance and safety | UGX 4.000.000 | Basic QC only |
| Launch labour, security, administration | UGX 7.000.000 | Opening month reserve |
| Sales, local transport, customer visits | UGX 3.000.000 | Launch campaign |
| Unallocated cash buffer | UGX 2.000.000 | Do not spend unless necessary |
| TOTAL | UGX 130.000.000 | Exactly within the cap |

Excluded from the Phase 1 budget Land purchase, owned delivery truck, ready-mix plant, transit mixer, heavy culvert moulds, crane/forklift, second line, large laboratory equipment, regional depots and the founder's private costs.

# 19. Financial Model and Monthly Result

The model uses 26 working days per month and the defined sales mix. Monthly revenue of UGX 140,020,000 requires the sale of 44,000 products plus UGX 1,620,000 in delivery charges. All values are before financing cost, and tax is a simplified illustration.

| Monthly line item | UGX | % of revenue |
| --- | --- | --- |
| Revenue | UGX 140.020.000 | 100.0% |
| Production/material cost | UGX 93.701.422 | 66,9% |
| Gross profit | UGX 46.318.578 | 33,1% |
| Operating expenses | UGX 14.100.000 | 10,1% |
| Operating profit before tax | UGX 32.218.578 | 23,0% |
| Illustrative corporation tax at 30% | UGX 9.665.573 | 6,9% |
| Illustrative profit after tax | UGX 22.553.005 | 16,1% |

Figure 4: Planned selling price and full cost per unit. 60 mm pavers and solid blocks require particularly strict pricing discipline.

| Product | Planned price | Full cost | Unit contribution | Margin | Status |
| --- | --- | --- | --- | --- | --- |
| 6-inch hollow blocks | UGX 2.600 | UGX 1.796 | UGX 804 | 30,9% | Estimated |
| 8-inch hollow blocks | UGX 3.400 | UGX 2.264 | UGX 1.136 | 33,4% | Estimated |
| solid blocks | UGX 3.000 | UGX 2.551 | UGX 449 | 15,0% | Estimated |
| 60 mm pavers | UGX 2.400 | UGX 2.112 | UGX 288 | 12,0% | Quotation Required |
| 80 mm pavers | UGX 3.200 | UGX 2.400 | UGX 800 | 25,0% | Quotation Required |
| kerbstones | UGX 18.000 | UGX 9.261 | UGX 8.739 | 48,5% | Estimated |

# 20. Break-even, Profit Target and Sensitivity

The integrated model produces monthly break-even revenue of UGX 42,623,977. The more important management threshold is the target profit: at the same gross margin, approximately UGX 103,083,519 of monthly revenue is required for UGX 20,000,000 of pre-tax profit. For a simplified UGX 20,000,000 profit after 30% model tax, the revenue threshold rises to approximately UGX 128,994,751.

| Scenario | Assumptions | Revenue | Total cost | Pre-tax profit | Model profit after tax |
| --- | --- | --- | --- | --- | --- |
| Downside | 65% volume; -5% price; +8% unit cost; +5% OPEX | UGX 86.462.350 | UGX 80.583.398 | UGX 5.878.952 | UGX 4.115.266 |
| Base model | Defined sales mix and current assumptions | UGX 140.020.000 | UGX 107.801.422 | UGX 32.218.578 | UGX 22.553.005 |
| Upside | +10% volume; +3% price; -2% unit cost; +8% OPEX | UGX 158.642.660 | UGX 116.238.133 | UGX 42.404.527 | UGX 29.683.169 |

Figure 5: The UGX 20 million target is achieved in the base model but missed materially in the downside case.

Management response in the downside case Stop expansion investment, produce 60 mm pavers only against orders, review prices weekly, buy inputs in smaller tranches, suspend credit sales and concentrate machine and staff time on profitable core products.

# 21. Financial Plan 2026-2035

The plan treats 2026 as a preparation, financing and procurement year with no operating revenue. The first full operating year is 2027 at an average 70% of stable base utilisation. From 2031, limited capacity expansion from retained earnings is assumed. Revenue and production cost escalate by 3% a year and operating expenses by 5%. Expansion capital expenditure, depreciation, financing and specific tax deductions are excluded.

| Year | Utilisation | Revenue | Total cost | Pre-tax profit | Model profit after tax |
| --- | --- | --- | --- | --- | --- |
| 2026 | Preparation | UGX 0 | UGX 0 | UGX 0 | UGX 0 |
| 2027 | 70% | UGX 1.18 Mrd. | UGX 956.3 Mio. | UGX 219.9 Mio. | UGX 153.9 Mio. |
| 2028 | 85% | UGX 1.47 Mrd. | UGX 1.16 Mrd. | UGX 309.0 Mio. | UGX 216.3 Mio. |
| 2029 | 95% | UGX 1.69 Mrd. | UGX 1.32 Mrd. | UGX 373.6 Mio. | UGX 261.6 Mio. |
| 2030 | 100% | UGX 1.84 Mrd. | UGX 1.42 Mrd. | UGX 411.5 Mio. | UGX 288.0 Mio. |
| 2031 | 105% | UGX 1.99 Mrd. | UGX 1.53 Mrd. | UGX 451.2 Mio. | UGX 315.8 Mio. |
| 2032 | 110% | UGX 2.14 Mrd. | UGX 1.65 Mrd. | UGX 492.8 Mio. | UGX 345.0 Mio. |
| 2033 | 115% | UGX 2.31 Mrd. | UGX 1.77 Mrd. | UGX 536.5 Mio. | UGX 375.5 Mio. |
| 2034 | 120% | UGX 2.48 Mrd. | UGX 1.90 Mrd. | UGX 582.2 Mio. | UGX 407.6 Mio. |
| 2035 | 125% | UGX 2.66 Mrd. | UGX 2.03 Mrd. | UGX 630.1 Mio. | UGX 441.1 Mio. |

Figure 6: Ten-year planning model. Values after 2031 assume capacity additions financed from retained cash flow.

# 22. Financing and Capital Strategy

The total requirement is UGX 130,000,000. Suitable funding may combine grant support, patient equity, a shareholder loan, equipment finance or supplier credit. Valuation and equity percentage should be set only after the site, quotations, customer evidence and legal structure are documented.

| Capital source | Suitability | Protection condition |
| --- | --- | --- |
| Grant/impact award | Useful for prototype, testing and environmental action | Avoid dependence on a single competition |
| Patient equity | Suitable for long-term industrial build | Written valuation, governance and exit rights |
| Shareholder loan | Clear repayment while founder retains control | Repayment only from sufficient cash flow |
| Equipment/supplier finance | Reduces immediate cash requirement | Verify total cost, guarantees and title |
| Customer deposits | Strengthens working capital and validates demand | Clear delivery schedule and secure custody |

The theoretical run-rate profit could imply a very short payback period, but this document does not present that number as a return promise. The operating objective is payback within 12 to 18 months after commercial start, subject to ramp-up, tax, rejection, working capital, investor terms and reinvestment.

# 23. Risk Register

| Risk | Likelihood | Impact | Control |
| --- | --- | --- | --- |
| Machine offer exceeds UGX 45m | High | High | Three comparable quotations; reduce specification rather than use buffer |
| Site rights not secured | Medium | High | Signed lease/use right and land-use review before order |
| Sales below plan | High | High | Interviews, letters of intent, deposits and weekly pipeline |
| Cement/input inflation | High | High | Frequent pricing, quotation validity and escalation clauses |
| Paver contribution too low | High | Medium | Order-only production with minimum contribution |
| Quality or curing failure | Medium | High | Batch limits, tests, training and external reference tests |
| Machine breakdown | Medium | High | Maintenance plan, spare-parts pack and service clause |
| Power/water interruption | Medium | High | Storage, alternatives, load plan and emergency operation |
| Payment delay | Medium | High | Deposits, credit limits, due-date control and delivery stop |
| Approval delays | Medium | High | Early URSB, URA, NEMA, local authority, OSH and UNBS checks |
| Founder operates remotely | Medium | High | Local accountable lead, digital control and clear authority |
| Fraud or inventory loss | Medium | High | Segregated duties, counts, document trail, access control and banking |
| Premature expansion | Medium | High | Defer ready-mix, culverts and specialist moulds until gates are met |

# 24. Decision Gates and 90-Day Work Plan

Site file: ownership/lease evidence, plan, access, power, water, drainage and neighbour conditions.

Legal file: URSB incorporation route, TIN, trading licence and NEMA, OSH and UNBS pre-consultation.

Procurement file: three machine quotations, three mould quotations, warranty, spare parts, training and acceptance plan.

Market file: 20 interviews, five letters of intent or credible quotation requests and three price checks per core product.

Finance file: UGX 130 million budget, milestone drawdown, bank account and evidence/approval rules.

Quality file: work instructions, sampling plan, curing register, release tests and complaint process.

People/governance file: local roles, contracts, authority, controls and reporting frequency.

| Gate | Required condition | Action if not met |
| --- | --- | --- |
| G1 Finance | UGX 130m committed and milestone drawdown agreed | Do not order |
| G2 Site | Rights, approval path and connections confirmed | Change site or renegotiate |
| G3 Machine | Capacity, moulds, power, warranty and cost documented | Reduce specification or supplier |
| G4 Market | Letters/quotations support the core sales plan | Reduce start volume and raw stock |
| G5 Quality | Trial mixes and release criteria passed | Do not sell; adjust recipe/process |
| G6 Expansion | Six positive cash-flow months and confirmed orders | Continue starter portfolio |

# 25. Conclusion

MICPF is financeable in principle as a lean starter project restricted to core products. Its strength is the combination of local demand validation, production discipline, documented quality and digital management. The critical success factor is controlled execution of four core products, positive unit contribution, customer deposits and strict adherence to the investment ceiling.

The next sensible decision is conditional financing rather than immediate full investment. Once the six gates are supported by evidence, Phase 1 can proceed and later be updated using actual monthly data.

Recommendation for startup advisory Support the founder with financing strategy, investor readiness, relevant networks, Green Impact Award preparation, governance and realistic milestone funding. The venture remains a Ugandan company; German programmes should be pursued only where site and commercialisation conditions are genuinely satisfied.

# Appendix A: Assumptions and Data Register

| Category | Planned value/claim | Status | Next evidence |
| --- | --- | --- | --- |
| Budget | UGX 130m; UGX 128m essential; UGX 2m buffer | Internally reconciled | Funding commitment and use-of-funds plan |
| Machine | UGX 45m | Quotation required | Three written quotations |
| Moulds | UGX 14m | Quotation required | Mould list and service life |
| Site | Mbarara; no land purchase in budget | Open | Title/lease and authority pre-check |
| Monthly revenue | UGX 140.02m | Estimated | Letters, orders and capacity evidence |
| Monthly pre-tax profit | UGX 32.219m | Model value | Actuals after three months |
| Product prices | See financial model | Estimated/quotation required | Dated market quotations |
| Input prices | See Section 11 | Estimated | Supplier quotations and weighbridge evidence |
| Competitors | Starting list | Needs verification | Field visit, phone, website or quotation |
| Taxes | 30% simplified model tax | Official rate; application to verify | Ugandan tax adviser |

# Appendix B: Sources

| ID | Source | Use/link |
| --- | --- | --- |
| S1 | MICPF Funding Data, 9 July 2026 | Local project file; budget, costing and metrics |
| S2 | MICPF seedData.ts / calculations.ts | Local integrated data and calculation model |
| S3 | MICPF Master Report 2026-2035 | Structure and context only; stale financial figures excluded |
| S4 | FAU Spin-off Advisory Checklist | Founder profile, motivation, idea and advisory needs |
| S5 | Uganda Registration Services Bureau | https://ursb.go.ug/services/business-registration/ |
| S6 | Uganda Revenue Authority: Formalisation/TIN | https://ura.go.ug/en/business-formalisation/ |
| S7 | NEMA: Project Brief and ESIA | https://www.nema.go.ug/en/project-brief/ |
| S8 | UNBS Product Certification | https://unbs.go.ug/content.php?pg=content&src=product-certification |
| S9 | UNBS US 2032:2019 Hollow concrete block | https://webstore.unbs.go.ug/store.php?preview=&src=3873 |
| S10 | UNBS US 65:2019 Precast paving units | https://webstore.unbs.go.ug/store.php?preview=&src=3872 |
| S11 | URA Corporation Tax | https://ura.go.ug/en/corporation-tax/ |
| S12 | URA VAT registered category / EFRIS | https://ura.go.ug/en/vat-registered-category/ |
| S13 | MGLSD OSHMIS Workplace Registration | https://oshmis.mglsd.go.ug/ |
| S14 | NSSF Uganda Employer Registration | https://www.nssfug.org/media-center/resource-center/resource-center/ |

# Appendix C: Verification and Disclaimer

This business plan is not a promise of funding, return, certification or market success. It is based on the current integrated project model and clearly labelled assumptions. Machinery cost, input price, selling price, competitor information, site rights, construction and environmental requirements, product standards, tax treatment and supplier terms must be reconfirmed before binding contracts. The model tax is not tax advice, and the technical mixes are not certified recipes or structural designs.

Mbarara Integrated Concrete Products Factory | Hillary Arindamukama | August 2026